## Cost Estimation
Cost Estimation — Outpatient Wait-Time AI System
Mindtone Mental Health Clinic ¦ Figures in USD ¦ Blue cells are editable assumptions
A. One-Time Development Costs (Pilot Build)
Phase | Duration (weeks) | Team size (FTE) | Hrs/week per FTE | Estimated hours | Blended rate ($/hr) | Cost ($)
Discovery & requirements | 2 | 1.5 | 40 | 120 | 65 | 7800
Data collection & integration | 3 | 1 | 40 | 120 | 70 | 8400
Model development (wait-time engine) | 3 | 1 | 40 | 120 | 85 | 10200
Queue optimizer & scheduling logic | 3 | 1 | 40 | 120 | 75 | 9000
Dashboard & patient app (UI) | 3.5 | 1.5 | 40 | 210 | 70 | 14700
Integration & pilot (Psychiatry dept.) | 2.5 | 1.5 | 40 | 150 | 70 | 10500
Staff training & feedback loop | 2 | 1 | 40 | 80 | 55 | 4400
Full rollout (all departments) | 1.5 | 1 | 40 | 60 | 70 | 4200
Monitoring & optimization (mo. 1) | 2 | 1 | 40 | 80 | 75 | 6000
Total — One-time development |  |  |  | 1060 |  | 75200
B. Ongoing Monthly Costs (Post-Launch)
Item | Monthly cost ($)
Cloud hosting & infrastructure | 300
Model monitoring & scheduled retraining (part-time ML eng.) | 800
SMS / WhatsApp notification gateway fees | 150
Support & maintenance (allocated) | 600
Total monthly ongoing cost | 1850
C. Year 1 Total Investment Summary
One-time development (Section A) | 75200
Ongoing costs — 11 months post-pilot | 20350
Year 1 total investment | 95550
Note: rates and durations (blue cells) are estimates for planning; confirm actual vendor/staff rates during discovery.

## Development Timeline
Development Timeline — 14-Week Plan
Mindtone Mental Health Clinic ¦ Start = weeks elapsed from project kickoff. End date computed from Start + Duration.
Phase | Start (week) | Duration (weeks) | End (week) | Key deliverable
1. Discovery & requirements | 0 | 2 | 2 | Signed-off requirements & data audit
2. Data collection & integration | 1.5 | 3 | 4.5 | Unified Mindtone dataset
3. Model development (wait-time engine) | 3.5 | 3 | 6.5 | Validated prediction model (MAE/RMSE/R2 report)
4. Queue optimizer & scheduling logic | 4.5 | 3 | 7.5 | Working optimizer against historical data
5. Dashboard & patient app (UI) | 5 | 3.5 | 8.5 | Staff dashboard + patient wait-time view
6. Integration & pilot (Psychiatry dept.) | 8 | 2.5 | 10.5 | Live pilot in Psychiatry
7. Staff training & feedback loop | 9 | 2 | 11 | Trained staff, documented feedback
8. Full rollout (all departments) | 10.5 | 1.5 | 12 | Psychiatry, Counseling & Addiction Therapy live
9. Monitoring & optimization | 12 | 2 | 14 | Drift monitoring & first retrain cycle
Total project duration (weeks) |  |  | 14